## Sheet1
Activity | Estimated Duration (WEEKS) | Actual Finish | Time (actual weeks) | Planned Progress | Actual Progress
A | 2 | 2 | 0 | 0 | 0
B | 5 | 4 | 5 | 7.0588 | 17
C | 7 | 6 | 10 | 14.1176 | 24
D | 1 | 1 | 15 | 21.1765 | 24
E | 4 | 4 | 20 | 28.2353 | 24
F | 2 | 2
G | 3 | 3
Sum of Task Durations | 24
Planned Project Duration | 17
Planned Progress per Day | 1.4118
Note on B11: Where did we get this from? In principle, this comes from our AOA or AON graph, but just take it as given in this scenario.