## 1. Burn-up Charts
Task | Estimated Duration (days) | Actual Finish | Time (actual day) | Planned Progress | Actual Progress
1. Orbital Mechanics | 20 | 31 | 0 | 0 | 0
2.1. Time Tracking | 2 | 1 | 5 | 11.5823 | 20
2.2. Camera Angle | 3 | 4 | 10 | 23.1646 | 23
2.3. Camera Fly-Through | 8 | 4 | 15 | 34.7468 | 28
2.4. Bookmarks | 2 | 2 | 20 | 46.3291 | 28
3.1. Orbit Visualisation | 5 | 3 | 25 | 57.9114 | 41
3.2. Textures | 5 | 11 | 30 | 69.4937 | 41
3.3. Popup Labels | 3 | 9 | 35 | 81.0759 | 61
4.1. Planet Rendering | 13 | 24 | 40 | 92.6582 | 69
4.2. Star Rendering | 8 | 35 | 45 | 104.2405
4.3. Asteroid Rendering | 20 |  | 50 | 115.8228
4.4. Spacecraft Rendering | 20 |  | 55 | 127.4051
5.1. Solar System Data Entry | 13 |  | 60 | 138.9873
5.2. Star/Galaxy Data Entry | 40 |  | 65 | 150.5696
5.3. Extrasolar Planet Data Entry | 13 |  | 70 | 162.1519
5.4. Spacecraft Data Entry | 8 |  | 75 | 173.7342
|  |  | 80 | 185.3165
Sum of Task Durations | 183 |  | 85
Planned Project Duration | 79 |  | 90
Planned Progress per Day | 2.3165 |  | 95
100
b. In order to get to know how the project went: - I compare the planned and actual progress: + On day 10: the actual progress was 13, while the planned progress was over 23 + From day 30 to day 70: eventhough starting with 110 compared to only 70 of planned progress, the actual progress undergone 2 period of remaining unchanged and reached merely 121, whereas the planned progress reached over 160 on the 70th day. + Regarding to planned progress, it just took 80 days for completing. As for actual progress, it was 100 days which was out of the expectation. - Conclusion: The project progress is too slow as compared to the planned progress.
c. What I can draw from the graph at this point: + On day 40 of the project: the actual progress was approximately 70, while the planned progress was up to 93 + From day 25 to day 30: the actual progress remained constant at 40, whereas the planned progress jumpped from nearly 58 to 70. - Conclusion: Things are going badly. The project progress is far left behind (so slow) as compared to the planned progress. Before it is too late, I think we need to boost the productivity of the whole team for meeting the deadline, or negotiate with client for more time to complete, or negotiate with client for less scope ( whether or not they accept a product with less functionality or lower quality, and so forth).
Note on B20: Where did we get this from? In principle, this comes from our AOA or AON graph, but just take it as given in this scenario.

## 2. Kanban Boards
(a) What does this mean for our (current) ability to code, review and merge new tasks? Answer: - If we have a WIP limit of three, It means it can only have 3 tasks only in Coding/Testing, Review and Awaiting merge. - We can not move another task from Todo to Coding/Testing and from Review to Awaiting merge ( beacause in Coding/Testing and Awaiting merge already had 3 imcomplelted tasks). - We can only move once one task in Coding/Testing or in Awaiting Merge have to complete.
(b) Say our client wants “Spacecraft Rendering” to be completed as soon as possible. If we ignore potential task dependencies, but keep to the WIP limit, what would we need to do here?
Answer: Because the potential task dependencies are ignores and we just pay attention to the WIP limit ( limit of three), if we want to start doing " Space Rendering" task, we have to wait untill one task in Coding/Testing finish ( because there are 3 limit tasks) then we have right to start working with "Space Rendering". The same as Review and Awaiting Merge, if "Space Rendering" task enter to Review or Awaiting Merge stage and they are full of three tasks which are doing, the "Space Rendering" have to wait untill one task being done ( mean only have 2 task for a stage) can "Space Rendering" continue. Moreover, in order to complete "Space Rendering" task as soon as possible, we have to divide the workload for the project team evenly. Each team should take responsibility for each stage: Coding/Testing, Review and Awaiting Merge, once one task being done by a team in the previous stage, this task will be tranfer to another team at later stage. This makes sure everyone will work , do not waste time as well as ensure the project progress.
(c) At a minimum (in order to adhere to WIP limit), how many other tasks will end up in the “Done” column once we’re done with “Spacecraft Rendering”? | Todo | Coding/Testing | Review | Awaiting Merge | Done |  | Todo | Coding/Testing | Review | Awaiting Merge | Done |  | Todo | Coding/Testing | Review | Awaiting Merge | Done |  | Todo | Coding/Testing | Review | Awaiting Merge | Done |  | Todo | Coding/Testing | Review | Awaiting Merge | Done |  | Todo | Coding/Testing | Review | Awaiting Merge | Done |  | Todo | Coding/Testing | Review | Awaiting Merge | Done
Answer: 2 minimum tasks will be end up in "Done" colum ( not include "Space Rendering") | Planet Rendering | Orbit Visualisation | Camera Fly-Through | Orbital Mechanics |  |  | Planet Rendering | Textures | Camera Fly-Through | Orbital Mechanics |  |  | Planet Rendering | Spacecraft Rendering | Camera Fly-Through | Orbital Mechanics |  |  | Planet Rendering | Textures | Spacecraft Rendering | Time Tracking | Orbital Mechanics |  | Planet Rendering | Textures | Spacecraft Rendering | Time Tracking | Orbital Mechanics |  | Planet Rendering | Textures | Bookmarks | Spacecraft Rendering | Orbital Mechanics |  | Planet Rendering | Textures | Bookmarks | Camera Angle | Orbital Mechanics
The process beside describes for the process of completing "Space Rendering" | Star Rendering | Textures | Bookmarks | Time Tracking |  | → | Star Rendering | Popup Labels | Bookmarks | Time Tracking |  | → | Star Rendering | Textures | Bookmarks | Time Tracking |  | → | Star Rendering | Popup Labels | Bookmarks | Camera Angle |  | → | Star Rendering | Popup Labels | Bookmarks | Camera Angle |  | → | Star Rendering | Popup Labels | Orbit Visualisation | Camera Angle | Time Tracking | → | Star Rendering | Popup Labels | Orbit Visualisation | Camera Fly-Through | Time Tracking
| Asteroid Rendering | Popup Labels |  | Camera Angle |  |  | Asteroid Rendering |  | Orbit Visualisation | Camera Angle |  |  | Asteroid Rendering | Popup Labels | Orbit Visualisation | Camera Angle |  |  | Asteroid Rendering |  | Orbit Visualisation | Camera Fly-Through |  |  | Asteroid Rendering |  | Orbit Visualisation | Camera Fly-Through |  |  | Asteroid Rendering |  |  | Camera Fly-Through |  |  | Asteroid Rendering |  |  |  | Spacecraft Rendering
| Spacecraft Rendering | [5 empty] | Spacecraft Rendering
(d) Would this number reflect what is actually likely to happen? Why, or why not?
Answer: This number tell us the situation is tht company will pause a task in each coloum to quickly push this project through every step. Therefore, the company still works at normal speed but in different order of tasks to make client satisfied. Moreover, the number of WIP limit reflect the progress of the whole project. If we increase the WIP limit, working progress limit will all increase completion time for the project. However, if the project team have to do a lot of works at the same time, I can directly to the project quality
(e) Say that “Spacecraft Rendering”is finally merged, and thus in the Done column, but the client is not satisfied with the result. How would we handle this? | Todo | Coding/Testing | Review | Awaiting Merge | Done
Answer: We should re-assign the problem to todo list, add more cards to the mid project and discover problems that need to be fixed in order to fix the problem that makes the client not happy. | Planet Rendering | Orbit Visualisation | Camera Fly-Through | Orbital Mechanics
| Star Rendering | Textures | Bookmarks | Time Tracking
| Asteroid Rendering | Popup Labels |  | Camera Angle
Spacecraft Rendering
Bugfix: unhappy problem
(f) Your team has decided that, in future projects, each task will have associated documentation written for it. For instance, for “Time Tracking” (if it were to be done again) there would be a section in the user manual describing how it works. To write this documentation properly, the code first needs to have been completed. The documentation needs to be subject to review and merging (along with the code). How would you adjust the kanban process to represent this?
| Todo | Coding/Testing | Review | Awaiting Merge | Done |  | Todo | Coding/Testing | Review | Awaiting Merge | Done |  | Todo | Coding/Testing | Review | Awaiting Merge | Done |  | Todo | Coding/Testing | Review | Awaiting Merge | Done
|  | Time tracking | [5 empty] | Stop watch | Time tracking |  |  |  |  | Car Rendering | Stop watch | Time tracking |  |  |  | Time tracking doc | Car Rendering | Stop watch | Time tracking
Answer: The Kanban process as besides | Time tracking doc |  |  |  |  | → | Time tracking doc |  |  |  |  | → | Time tracking doc |  |  |  |  | →
Stop watch
| Car Rendering | [5 empty] | Car Rendering
(g) On a different note, say you wanted to use a kanban board for studying ISE topics. What would it look like?
Answer: | Todo | Doing | Done |  | Todo | Doing | Done |  | Todo | Doing | Done |  | Todo | Doing | Done
The series of chart besides are kanban board for studying a ISEN topic. |  | Research for the topics at home |  |  |  | Attend tutorial classes | Research for the topics at home |  |  | Practice with assigments | Research for the topics at home |  |  |  | Research for the topics at home
WIP limit of two |  | Listen to the lectures |  |  |  | Consult with lecturer | Listen to the lectures |  |  | Take the tests | Listen to the lectures |  |  |  | Listen to the lectures
| Attend tutorial classes | [9 empty] | Attend tutorial classes |  |  |  | Attend tutorial classes
Todo list initially: Research for the topics at home, Listen to the lectures, Attent tutorial classes, Consult with lecture, Practise with assigments, Take the tests | Consult with lecturer |  |  | → |  |  |  | → |  |  | Consult with lecturer | → |  |  | Consult with lecturer
| Practice with assigments |  |  |  | Practice with assigments | [9 empty] | Practice with assigments
| Take the tests |  |  |  | Take the tests | [9 empty] | Take the tests

## 3. Scrum
(a) Say you’re working with a Scrum sprint length of 4 weeks, and that period has come to an end. Over the next two days: (i) What are the key events that take place? - Sprint Review (a 1/2 day meeting at the end of a sprint): The developers show the customer what has been done. - Sprint Retrospective (another 1/2 day meeting right after the sprint review): The developers discuss how well things went, and what might be improved. This is about the team itself, not the product. - Daily Scrum or “stand-up” (a 15-minute meeting at the start of each day): The developers discuss their planned work for the day. (ii) What are the responsibilities of the scrum master, the product owner, and the de- velopment team in these events? - Scrum Master: helps the team follow Scrum + They must be on top of all the Scrum practices. + They must understand what should happen when, and make sure everyone else is aware of this. - Product Owner: helps the team make the right product + They make sure user stories are correct, and decide which have the highest priority. + The PO is not the customer. - Development Team (3–9 software developers): writes the software + They take user stories and implement them.
(b) Where would planning poker fit into Scrum? Answer: Planning poker is a game performed by all team members to estimate the time and effort necessary to execute a job. According to that, resources are allotted to each task. If it is determined that a job will need a significant amount of work during the planning poker phase, additional resources will be allotted to that activity. Thank to that, we will have an reliable estimation of how long the sprint will last.
(c) How does Scrum handle changes to requirements, mid-way through a project? Who is immediately responsible? Answer: Sprint Master is the one who immediately takes reponsibility. They need to access the new goal and determine how long it will take to complete, then stop the current sprint. From that point, they should start doing the new sprint and appoint the new task for developer team. Generally, they just have to create extra documentation on the task that was completed during the previous scrum and keep going on the changes.